## AAB start
Name: |  | Bernard Swanepoel
Student number: |  | 39909476
Please select the approximate unit price for the product you have chosen:
(select)
unit price < R100
R100 ≤ unitprice < R1000
unit price ≥ R1000
1. Use this data for a)-d):
Annual demand (D) = |  |  | 200 |  |  |  | R100 ≤ unitprice < R1000
Work days per year = |  |  | 176
Ordering cost (Co) = |  |  | 16
Carying cost (Ch) = |  |  | 4 | % of the unit price
Unit price (P) = |  |  | 4
Lead time (L) = |  |  | 12
e) Setup cost (Cs) = |  |  | 40
Daily production rate (p) = |  |  | 4
f) Number of units ordered = |  |  | 24
2. Activity |  |  |  | Duration (weeks) | Predecessor(s) | Activity cost (Rands)
A. Write instructions |  |  |  | 4 | - | 3000
B. Select operators |  |  |  | 4 | - | 3000
C. Train operators |  |  |  | 4 | A, B | 4000
D. Announce new service |  |  |  | 5 | B | 4000
E. Purchase, ship, and receive equipment |  |  |  | 7 | - | 12000
F. Test new operators on equipment |  |  |  | 2 | C, E | 4000
1. This question relates to one of the products that your company provides. Select the approximate price range for this product above and generate your data. The annual demand (D) is constant throughout the year. Use the information provided for each part of the question.
2. You decide to prepare for the manufacturing process while your analysis is being done. You identify the following steps for this process:
(1) write instructions and procedures,
(2) select techniques to operate the equipment, and
(3) procure the equipment.
The instructions and selection of the operators has to be completed before the training could commence. It is also necessary to choose the operators and evaluate their qualifications before formally announcing the new service to the local community. Upon arrival and installation of the equipment and completion of the operators' training, you will have to spend a period checking out the procedures, operators, and equipment before declaring that the project was successfully completed. Find your data in cells A33 through G39.

## Question1
1. Use this data for a)-d):
Annual demand (D) = | 200 |  | a. | EOQ
Work days per year = | 176 |  |  | 200 | units
Ordering cost (Co) = | 16 |  | b. | Number of order per year:
Carying cost (Ch) = | 4 | % of the unit price |  | 1 | orders
Unit price (P) = | 4 | 0.16 | c. | ROP
Lead time (L) = | 12 |  |  | 13.6364 | units
e) Setup cost (Cs) = | 40 |  | d. | Lead time (L) | 36
Daily production rate (p) = | 4 |  |  | New ROP | 40.9091 | units
f) Number of units ordered = | 24 |  |  | This ROP is much higher
Daily demand rate(d) = | 1.1364 |  | e. | Optimal production quantity:
|  |  |  | 373.7413 | units
|  |  | f. | Annual Co
133.3333

## Question2a
2. Activity | Duration (weeks) | Predecessor(s) | Activity cost (Rands) |  |  | ES+t
A. Write instructions | 4 | - | 3000 | Activity | ES | EF | LS | LF | LS-ES | CRIT
B. Select operators | 4 | - | 3000 | A | 0 | 4 | 0 | 4 | 0 | CRITICAL
C. Train operators | 4 | A, B | 4000 | B | 0 | 4 | 1 | 5 | 1 | NOT CRITICAL
D. Announce new service | 5 | B | 4000 | C | 4 | 8 | 4 | 8 | 0 | CRITICAL
E. Purchase, ship, and receive equipment | 7 | - | 12000 | D | 4 | 9 | 5 | 10 | 1 | NOT CRITICAL
F. Test new operators on equipment | 2 | C, E | 4000 | E | 0 | 7 | 1 | 8 | 1 | NOT CRITICAL
|  |  |  | F | 8 | 10 | 8 | 10 | 0 | CRITICAL
[5 empty] | product: | 10
a.)
F 2
8 10
8 10
Start
End
A 4
0 4
0 4
B 4
0 4
1 5
E 7
0 7
1 8
C 4
4 8
4 8
D 5
4 9
5 10

## Question2b,c,d
2. Activity |  |  |  | Duration (weeks) | Predecessor(s) | Activity cost (Rands)
A. Write instructions |  |  |  | 4 | - | 3000 |  |  | Activity | Cost | Week Saved
B. Select operators |  |  |  | 4 | - | 3000 |  |  | A. Instructions | 1000 | 1
C. Train operators |  |  |  | 4 | A, B | 4000 |  |  | C. Training | 1000 | 1
D. Announce new service |  |  |  | 5 | B | 4000 |  |  | E. Express Truck | 2000 | 1
E. Purchase, ship, and receive equipment |  |  |  | 7 | - | 12000 |  |  | E. Air Fright | 4000 | 2 |  | LEGEND
F. Test new operators on equipment |  |  |  | 2 | C, E | 4000 |  |  |  | 8000 |  |  | red text | Indicates a PERT setup which attempts to minimise the costs with the project crashing
Key:
Crash
| Not crash just used to calculate the PERT table | [10 empty] | Critical
|  |  | Time |  | Cost | [6 empty] | Normal
| b) | Activity | Normal | Crash | Normal | Crash | Crash Cost | [7 empty] | TRYING TO MINIMIZE COST FOR THE BEST RESULTS POSSIBLE
|  | A | 4 | 3 | 3000 | 4000 | 1000 | [6 empty] | Act | ES | EF | LS | LF | LS-ES | CRIT
|  | B | 4 | 4 | 3000 | 3000 | [7 empty] | A | 0 | 4 | 0 | 4 | 0 | CRITICAL
|  | C | 4 | 3 | 4000 | 5000 | 1000 | b) | [5 empty] | B | 0 | 4 | 0 | 4 | 0 | CRITICAL
|  | D | 5 | 5 | 4000 | 4000 | [7 empty] | C | 4 | 7 | 4 | 7 | 0 | CRITICAL
|  | E | 7 | 4 | 12000 | 18000 | 2000 | [6 empty] | D | 4 | 9 | 4 | 9 | 0 | CRITICAL
|  | F | 2 | 2 | 4000 | 4000 | [7 empty] | E | 0 | 7 | 1 | 8 | 1 | NOT CRITICAL
[6 empty] | 38000 | [7 empty] | F | 7 | 9 | 7 | 9 | 0 | CRITICAL
ES+t
b) | Activity | ES | EF | LS | LF | LS-ES | CRIT
| A | 0 | 3 | 1 | 4 | 1 | NOT CRITICAL
| B | 0 | 4 | 0 | 4 | 0 | CRITICAL
| C | 4 | 7 | 4 | 7 | 0 | CRITICAL
| D | 4 | 9 | 4 | 9 | 0 | CRITICAL
| E | 0 | 4 | 3 | 7 | 3 | NOT CRITICAL
| F | 7 | 9 | 7 | 9 | 0 | CRITICAL
|  | product: | 9
F 2
7 9
7 9
Start
End
A 3
0 3
1 4
B 4
0 4
0 4
E 4
0 4
3 7
C 3
4 7
4 7
D 5
4 9
4 9